SEASIDE BEACON

Marketing Campaign Plan

Phase 1 Launch: Taking Chennai's Sunrise Forecast to the Masses

Prepared by: Kevin T

Contact: kevin.t1302@gmail.com

Date: February 2026

Timeline: March - May 2026 (Q2)

Budget: Near-zero (organic-first strategy)

# 1. Campaign Overview

Campaign Name: "Set That Alarm" — Seaside Beacon Phase 1 Launch

Summary: Introduce Seaside Beacon to Chennai's photography community, beach-goers, and morning enthusiasts through a 12-week organic-first campaign across Instagram, Reddit, and SEO, positioning it as the only service that tells you whether tomorrow's sunrise is worth waking up for.

### Primary Objective

Reach 500 free email subscribers and 25 premium subscribers by end of May 2026.

### Secondary Objectives

- Build an Instagram presence to 1,000+ followers with sunrise content

- Establish SEO authority for "Chennai sunrise" and related keywords

- Create a community feedback loop (photo submissions + prediction ratings) to improve algorithm accuracy

- Generate organic word-of-mouth among Chennai's photography groups

# 2. Target Audience

## 2.1  Primary: Chennai Photography Enthusiasts

Age 18-40, own a DSLR or care about phone photography, active on Instagram. They wake up early specifically for golden hour shots but have no reliable way to predict which mornings will deliver dramatic skies. They waste 5 AM alarms on flat, hazy mornings.

Pain points:

- No way to know if a sunrise will be colourful or flat before going

- Weather apps show temperature and rain, not sunrise quality

- Camera settings for dawn conditions require experience to get right

- Don't know which Chennai beach has the best conditions on any given day

Where they are: Instagram (photography hashtags), Reddit (r/Chennai, r/photography, r/itookapicture), WhatsApp photography groups, Chennai photography clubs, ECR/Marina early morning crowds.

## 2.2  Secondary: Chennai Beach-Goers & Morning People

Joggers, walkers, couples, tourists who visit Marina or Elliot's Beach regularly. They don't photograph professionally but appreciate a beautiful sunrise. They'd love to know which mornings are "worth it" without checking multiple weather apps.

Where they are: Instagram (Chennai lifestyle), Reddit r/Chennai, local Facebook groups, Google search ("Chennai sunrise time", "Marina Beach morning").

## 2.3  Tertiary: Travel & Tourism

Tourists visiting Chennai who search "best time to visit Marina Beach" or "Chennai sunrise". They discover Seaside Beacon through SEO and use it to plan one or two early mornings during their trip.

# 3. Key Messages

### Core Message

"Seaside Beacon tells you honestly whether tomorrow's sunrise is worth waking up for — and if it is, helps you capture it."

### Supporting Messages

| Message | Copy | Proof Point |
| --- | --- | --- |
| Never waste a 5 AM alarm | Stop guessing. Seaside Beacon scores every morning 0-100 so you know before you go. | 9-factor atmospheric analysis including aerosol depth, cloud layers, and pressure trends. |
| Honest, not hyped | We'll tell you to sleep in when conditions are flat. No fake excitement, no wasted mornings. | Clear verdicts: GO, MAYBE, or SKIP. Score of 30? We say skip. |
| Your photography guide | DSLR and mobile settings tailored to tomorrow's specific light. Golden hour timing down to the minute. | Rule-based camera settings calibrated to cloud cover, humidity, and visibility. |
| Made in Chennai | Built by a Chennai sunrise enthusiast, calibrated to our tropical conditions. India's first. | Scoring algorithm tuned for 13°N latitude, 85-92% baseline humidity. |

# 4. Channel Strategy

All channels are organic (zero ad spend). The strategy leverages the product's visual nature — sunrise photos are inherently shareable — and Chennai's active online communities.

| Channel | Why | Content Format | Effort | Priority |
| --- | --- | --- | --- | --- |
| Instagram | Primary home for sunrise photography. Visual-first platform. Chennai photography community is active here. | Daily sunrise photos (with score overlay), Reels (timelapse + score reveal), Stories (morning forecast), carousel tips | High | #1 |
| Reddit | r/Chennai (180K+), r/photography, r/itookapicture. High-trust, word-of-mouth driven. | Launch post (r/Chennai), weekly "best sunrise" posts, photo threads, AMA about the project | Medium | #2 |
| SEO / Blog | "Chennai sunrise time", "Marina Beach sunrise" get consistent search volume. Long-term organic traffic. | Blog posts: best Chennai sunrise spots, photography guide, how scoring works. Schema markup for sunrise times. | Medium | #3 |
| Telegram | Direct channel to engaged users. Bot already built. Premium conversion driver. | Daily forecasts, weekly highlights, community photo shares. AI chatbot for engagement. | Low (built) | #4 |
| WhatsApp | Chennai photography groups are active here. Viral sharing potential. | Share forecast screenshots and sunrise photos. Link to website. Word-of-mouth. | Low | #5 |
| Google Maps | Tourists search for Marina Beach, Covelong, etc. on Maps before visiting. | Create a Google Business profile or contribute sunrise guides to beach listings. | Low | #6 |

# 5. Content Calendar (12 Weeks)

## Phase A: Foundation (Weeks 1-4, March 2026)

Goal: Establish presence, build initial content library, seed communities.

| Week | Content | Channel | Goal | Notes |
| --- | --- | --- | --- | --- |
| 1 | Set up Instagram profile (bio, highlights, grid aesthetic). Post 5 sunrise photos with scores. | Instagram | Profile launch | Use best archived photos |
| 1 | Launch post on r/Chennai: "I built India's first sunrise quality forecast for our beaches" | Reddit | Awareness + feedback | Authentic, humble tone |
| 2 | "How Seaside Beacon Works" carousel (9 slides explaining the scoring algorithm simply) | Instagram | Education | Save-worthy content |
| 2 | Blog post: "5 Best Spots to Watch the Sunrise in Chennai" (SEO-optimised) | Website/SEO | Organic traffic | Target: chennai sunrise |
| 3 | First Reel: timelapse sunrise with score reveal overlay. Before/after comparison. | Instagram | Reach + engagement | Reels get 2-3x reach |
| 3 | Reddit r/photography post: share a high-score vs low-score comparison photo | Reddit | Photography community | "Can you tell which scored 85 vs 35?" |
| 4 | Blog post: "Why Some Sunrises Explode With Colour (And Others Don't)" — the science, simply | Website/SEO | Authority + SEO | Link from Instagram bio |
| 4 | Instagram Story series: "This Week's Scores" — daily forecast stories Mon-Sun | Instagram | Daily engagement habit | Start the routine |

## Phase B: Growth (Weeks 5-8, April 2026)

Goal: Build community, drive email signups, start converting free to premium.

| Week | Content | Channel | Goal | Notes |
| --- | --- | --- | --- | --- |
| 5 | "Sunrise of the Week" series launch — best community photo + score + conditions breakdown | Instagram | Community engagement | Feature user photos |
| 5 | Blog: "A Photographer's Guide to Chennai's Golden Hour" (DSLR + mobile settings guide) | Website/SEO | Premium value showcase | Teases premium features |
| 6 | Reddit AMA: "I analyse 9 atmospheric factors to predict sunrise quality. AMA." | Reddit r/Chennai | Trust + signups | Be genuine, answer everything |
| 6 | Instagram Reel: "Score 85 vs Score 35 — same beach, different morning" side-by-side | Instagram | Viral potential | Visual proof the score works |
| 7 | Collaborate with 2-3 Chennai photography accounts — share each other's sunrise content | Instagram | Cross-promotion | DM photographers directly |
| 7 | Blog: "Marina vs Covelong vs Elliot's — Which Chennai Beach Has the Best Sunrise?" | Website/SEO | Beach comparison SEO | Drives beach switchers |
| 8 | Instagram carousel: "What Your Phone Camera Settings Should Be at 6 AM" (free value post) | Instagram | Save + share | Practical, shareable |
| 8 | Email milestone: celebrate subscriber count publicly. "100 people now wake up smarter." | All channels | Social proof | Humble celebration |

## Phase C: Acceleration (Weeks 9-12, May 2026)

Goal: Hit 500 subscribers, 25 premium. Establish Seaside Beacon as the go-to sunrise resource for Chennai.

| Week | Content | Channel | Goal | Notes |
| --- | --- | --- | --- | --- |
| 9 | "Accuracy Report" post — how accurate were our predictions last month? (show real data) | All channels | Trust + credibility | Transparency builds trust |
| 10 | Instagram Reel: "I woke up at 5 AM for 30 days straight. Here's what I learned." (personal story) | Instagram | Emotional connection | Kevin's personal story |
| 11 | Blog: "How We Built India's First Sunrise Forecast" — the technical story, told simply | Website/Reddit | Indie dev community | Cross-post to r/SideProject |
| 12 | Campaign wrap: "Month 1 Results" — share growth, accuracy, best sunrises, community highlights | All channels | Momentum into Phase 2 | Set up Pondicherry tease |

# 6. Content Assets Required

| Asset | Type | Priority | Timeline | Notes |
| --- | --- | --- | --- | --- |
| Instagram profile setup (bio, highlights, grid plan) | Profile | Must-have | Week 1 | Bronze/dark aesthetic matching site |
| 10-15 curated sunrise photos with score overlays | Image | Must-have | Week 1-2 | Need a score overlay template |
| "How Scoring Works" carousel (9 slides) | Carousel | Must-have | Week 2 | Canva or similar |
| 3 Reels (timelapse + score reveal) | Video | Must-have | Week 3, 6, 10 | Record real sunrises + overlay |
| 4 SEO blog posts | Blog | Must-have | Week 2, 4, 5, 7 | 1,500-2,000 words each |
| Reddit launch post + AMA prep | Post | Must-have | Week 1, 6 | Authentic, no marketing speak |
| Score overlay template for Instagram | Design | Must-have | Week 1 | Reusable template with score + verdict |
| "Sunrise of the Week" post template | Design | Nice-to-have | Week 5 | Feature community photos |
| Accuracy report infographic | Design | Nice-to-have | Week 9 | Show prediction accuracy visually |
| "30 Days of Sunrises" Reel script | Script | Nice-to-have | Week 10 | Personal story format |

# 7. Success Metrics

| KPI | Target (12 weeks) | How to Track | Reporting |
| --- | --- | --- | --- |
| Free email subscribers | 500 | MongoDB subscriber count | Weekly |
| Premium subscribers | 25 | Razorpay dashboard + MongoDB | Weekly |
| Instagram followers | 1,000 | Instagram Insights | Weekly |
| Website daily visits | 200/day average | Admin dashboard (DailyVisit) | Weekly |
| Reddit post engagement | 500+ upvotes on launch post | Reddit directly | Per post |
| SEO rankings | Page 1 for "Chennai sunrise" | Google Search Console | Monthly |
| Email open rate | 40%+ | Brevo analytics | Weekly |
| Prediction accuracy rating | 70%+ "spot on" or "close" | Feedback collection (MongoDB) | Monthly |
| Community photo submissions | 50+ | SunriseSubmission collection | Monthly |
| Monthly revenue | INR 1,225+ (25 x INR 49) | Razorpay dashboard | Monthly |

# 8. Risks and Mitigations

| Risk | Likelihood | Mitigation |
| --- | --- | --- |
| Low engagement on Reddit/Instagram initially | High | Focus on quality over quantity. Post consistently for 4 weeks before evaluating. Engage genuinely in communities before promoting. |
| Prediction accuracy questioned publicly | Medium | Publish monthly accuracy reports proactively. Invite feedback openly. "We said 72, reality was closer to 50 — here's why" builds more trust than hiding misses. |
| Solo creator burnout (content + dev + support) | Medium | Batch content creation on weekends. Automate what's possible (daily forecast stories). Focus on 2 channels max in any given week. It's okay to skip a week. |
| Free tier is "good enough" — low premium conversion | Medium | Ensure premium feels genuinely valuable, not artificially gated. Photography settings and AI chatbot are real value. Emphasise the mission angle: "keeps this project alive." |
| Infrastructure limits hit (email capacity, API costs) | Low | 400 emails/day covers up to 200 subs on both plans. Premium revenue offsets costs. Monitor and plan upgrade path before hitting limits. |

# 9. Immediate Next Steps

This Week (Before Content Starts):

- Deploy the chatbot fixes (needsWeather regex + data labeling)

- Set ADMIN_TELEGRAM_CHAT_ID environment variable for support ticket notifications

- Create Instagram account (@seasidebeacon or @seaside.beacon)

- Design score overlay template for sunrise photos (dark theme, bronze accent, score + verdict)

- Photograph 10-15 sunrises at different beaches for initial content library

- Set up Google Search Console for seasidebeacon.com

- Draft the Reddit r/Chennai launch post

Week 1 Launch Checklist:

- Post first 5 photos on Instagram with scores

- Publish r/Chennai launch post

- Start daily Instagram Stories with morning forecast

- Share in 2-3 WhatsApp photography groups

- Monitor subscriber growth daily for first two weeks

# 10. SEO Keyword Targets

| Keyword | Intent | Difficulty | Content Plan |
| --- | --- | --- | --- |
| chennai sunrise time | Informational | Low | Add sunrise time to homepage + blog post |
| marina beach sunrise | Informational | Low | Dedicated blog post + beach page |
| best time to visit marina beach | Transactional | Medium | Blog post linking to daily forecast |
| chennai beach photography | Informational | Low | Photography guide blog post |
| sunrise forecast india | Navigational | Low | Homepage SEO + JSON-LD schema |
| covelong beach sunrise | Informational | Low | Beach comparison blog post |
| golden hour chennai | Informational | Low | Photography guide + homepage feature |

Seaside Beacon  |  kevin.t1302@gmail.com  |  www.seasidebeacon.com